## Slide 1: JLEIC pre-CDR (pCDR)
Deliverables/Milestones
    Document consistent design of JLEIC by end FY18
    Include appendix on 6T magnet option for energy reach competitiveness
      readiness for possible CY18 CD0 and Jul 30 2018 EIC User’s Group Meeting
      section rough draft target date May 31 2018
      diverse resources requested Feb-Sep 2018
    Staffing:
      FTEs: 2.2 CASA (30% of 7.4 MEPCDE), 2-3 engineering, 0.3 administrative, 1-2 other groups
      Scope: Separate Engineering, Rad Physics, Facilities scope meetings Feb 5-12
      When needed: CASA: throughout FY18; other groups, Feb-Aug 2018
Issues/Concerns that are/could affect on time delivery
    Facility integrated parameter milestone slip pushing coordination (2 wks)
    Engineering, facilities, ESH work require fixed beam parameter specifics
    Cryo resources likely minimal; address with cryo as technical reviewers
    Radiation physics resources: constrained with staff departures
Recommended Mitigation
  Reduce scope of document sections to match available resources