## Slide 1
Superconducting Magnet Rings for MEIC Mockup Winding Review

## Slide 2: Agenda

## Slide 3: Overview of Task 2
Objectives of Task 2:
Build a ~1.2 m mockup winding using the structural elements, CIC cable, and winding tooling appropriate for an actual MEIC dipole.
Evaluate the precision for locating each turn in the body of the winding.
Evaluate the procedures for forming the flared ends on each turn.
Evaluate the alternatives for the spring tube in the CIC cable, measure critical current in extracted strands from the formed ends.
Modifications in the objectives during the project:
Cost for procuring strand with properties specified for MEIC was not provided in the contract. In consultation with MEIC management, we opted to build the mockup winding with empty tube having the material and thickness for actual CIC, drawn to the finish dimension for the CIC.
Cost for fabrication of the G-11 structural elements was higher than foreseen. MEIC management authorized us to shorten the length of the mockup winding. We managed to find cost savings that enabled us to stay with the 1.2 m body length.

## Slide 4: Major activities to date
Structural elements for winding
Develop detailed fabrication print sets for all G-11 components. ✓
Contract fabrication of one body segment, QC fabricated part to qualify vendor. ✓
Contract for fabrication of all G-11 components, in 3 priority groups:
  Structural elements to be impregnated with beam tube and wind layer 1 ✓
  Structural elements needed to complete layer 2 
  Structural elements needed to complete layer 3 
Fabricate SS beam tube and flanking SS structural bars. ✓
Assemble priority 1 parts on beam tube and vacuum impregnate structural beam. ✓
Motorized bending tools
Develop piece-part prints for bending tools:
  Main bender for 180° U-bends ✓
  Compound bender for 90° flare bends with steps for transitions ✓
  Special benders for dog-bone ends and for close bends 
Fabricate main bender and compound bender, integrate with motor/gearbox assys✓
Develop control programs for the required bends. 
CuNi tube for dummy cable, draw to final cable diameter ✓
  Form sample cables, form 180° U-bends, extract strands, test Ic. ✓
  Develop 3D FEA model of the dipole, evaluate support for ends. 

## Slide 5: Update on magnetic, mechanical design
Rutherford-based design reported at EIC Cost Review 1/2015:
CIC-based design optimized to minimize sextupoles:

## Slide 6
Initially plan A MEIC dipole using Rutherford cable, 0.8 mm strands,
15 kA @ 3 T, bn<10 units
Became plan B and was not further optimized
Initial design
Design adjusted for conventional winding
Design adjusted for barrel winding
Design stages of Rutherford cable based 3T MEIC dipole

## Slide 7
Initial 3 T design
Initial 3.5 T @15kA design, conventional winding
3.5 T design, barrel winding
3.0 T design, barrel winding, b2<2 units (May)
Design stages of CiC based >3T MEIC dipole
Initially started as plan B, became plan A and further optimization steps were performed.

## Slide 8
Alternative approach: to improve transfer function, pole face was brought closer to the beam tube
Case 1, sextupole coil is inside of the pole region
Case 2, sextupole coil is outside of the pole region

## Slide 9
Improved version, all allowed multipoles <1 unit
As reported in August, all allowed multipoles <1.5 unit
Green is good!
13.7 kA @ 3.0 T, bn < 1 unit all fields

## Slide 10
I cable | 13.7 | kA
Estored | 64.15 | kJ/m
Inductance | 0.68 | mH/m
Bcoil | 3.49 | T
Tquench | 5.94 | K
ISSL | 19.7 | kA
Bcoil | 4.6 | T
Bbore | 3.85 | T
Nturns/bore | 2x12 | 
Nstrands | 15 | 
dstrands | 1.20 | Mm
Cu/Non Cu | 1.5 | 
Area | 8.23 | cm2
Expect ~1% SSL reduction due to solid conductor approximation.
Magnet will operate at 79% of SSL
(Fx kN/m, Fy kN/m) | (Fx kN/m, Fy kN/m) | (Fx kN/m, Fy kN/m) | (Fx kN/m, Fy kN/m)
(31.95,-3.06) (38.25,-3.47) | (30.24,-7.37) (36.13,-8.63) | (18.44,-7.65) (20.77,-8.23) | (4.19,-7.84) (4.97,-7.92)
 | (30.82,-3.26) (36.54,-3.74) | (18.29,-4.13) (20.80,-4.25) | (3.34,-4.40) (4.21,-4.38)
 | (31.61,0.98) (37.05,1.28) | (19.28,-0.86) (21.94,-0.71) | (3.54,-2.09) (4.42,-1.91)
 |  | (21.78,0.42) (24.56,0.47) | (4.33,-0.50) (5.03,-0.44)
Lorenz body forces on each turn of the MEIC dipole @ 3 T
(top set from 1.2 m 3d model, bottom set from 2d model):

## Slide 11
1.2m long straight section Symmetric 3D model of MEIC dipole at 2.92T central field
Max field in the conductor 3.33T (3.42T if scaled to 3T central field ) located at
(0.0242,0.042,0)
Location and magnitude (3.49T) of max field point is consistent with 2d simulations done in
COMSOL

## Slide 12
Multipoles due to cooldown and Lorenz forces
Simple thermal stress model was used to extract coil displacements at 4.2K 0T and 4.2K 3T
Turn index ij | Displacement (x,y) mil |  |  | 
 | Beam tube bonded to Coil Assembly |  | Beam tube mold released from Coil assembly | 
 | DCold | DCold+3T | DCold | DCold+3T
40 | (-3.48,-5.6) | (-3.03,-5.67) | (-3.22,-5.58) | (-2.56,-5.57)
41 | (-7.13,-4.85) | (-6.37,-4.93) | (-6.46,-4.71) | (-5.79,-4.81)
31 | (-7.15,-3.6) | (-6.19,-3.54) | (-6.35,-3.37) | (-5.54,-3.44)
21 | (-6.96,-2.12) | (-6.03,-2.1) | (-6.45,-2.04) | (-5.42,-1.99)
42 | (-8.53,-4.75) | (-7.54,-4.8) | (-7.79,-4.58) | (-7.01,-4.77)
32 | (-8.4,-3.42) | (-7.33,-3.42) | (-7.69,-3.29) | (-6.75,-3.40)
22 | (-8.28,-2.05) | (-7.21,-2.02) | (-7.50,-1.95) | (-6.68,-1.93)
12 | (-8.11,-0.63) | (-7.18,-0.63) | (-7.59,-0.66) | (-6.76,-0.57)
43 | (-9.74,-4.64) | (-8.76,-4.71) | (-8.99,-4.58) | (-8.33,-4.70)
33 | (-9.51,-3.16) | (-8.55,-3.36) | (-8.98,-3.25) | (-7.97,-3.35)
23 | (-9.39,-1.88) | (-8.43,-1.96) | (-8.80,-2.02) | (-7.91,-1.88)
13 | (-9.34,-0.76) | (-8.55,-0.55) | (-8.85,-0.62) | (-8.25,-0.61)
4.2K 3T
4.2K 0T

## Slide 13
Displacements ~ Force (forces are small enough)
Magnetic forces ~ B2 or ~I2
Displacements were parameterized as
Fields with displaced magnet parts were evaluated.
B, T | Db0 | Db1 | Db2 | Db3 | Db4 | Db5 | Db6 | Db7 | Db8 | Db9 | Db10
0.187 | -5.6e-4 | -6.9e-5 | 9.6e-2 | 5.5e-7 | -5.5e-2 | 9.0e-7 | 2.7e-2 | -9.8e-7 | -6.7e-3 | -9.7e-7 | -9.3e-4
0.374 | -1.1e-3 | 1.7e-6 | 9.5e-2 | -5.5e-7 | -5.5e-2 | 1.0e-6 | 2.7e-2 | -1.0e-6 | -6.7e-3 | -9.6e-7 | -9.3e-4
0.747 | -2.2e-3 | 1.4e-5 | 9.2e-2 | 2.8e-7 | -5.5e-2 | 1.1e-6 | 2.7e-2 | -1.0e-6 | -6.8e-3 | -9.6e-7 | -9.3e-4
1.121 | -3.3e-3 | -4.2e-5 | 8.7e-2 | -1.4e-5 | -5.4e-2 | 2.8e-6 | 2.7e-2 | -1.2e-6 | -6.8e-3 | -9.6e-7 | -9.2e-4
1.494 | -4.4e-3 | -4.6e-4 | 8.5e-2 | 6.1e-5 | -5.2e-2 | -5.3e-6 | 2.7e-2 | -5.2e-7 | -6.9e-3 | -9.8e-7 | -9.2e-4
1.863 | -5.3e-3 | -7.8e-3 | 1.0e-1 | 2.4e-3 | -5.5e-2 | -3.8e-4 | 2.8e-2 | 3.9e-5 | -7.2e-3 | -3.6e-6 | -9.0e-4
2.208 | -6.1e-3 | -4.5e-3 | 5.7e-2 | -4.1e-4 | -4.7e-2 | 7.4e-5 | 2.8e-2 | -9.2e-6 | -7.3e-3 | -2.7e-7 | -9.3e-4
2.513 | -6.9e-3 | -1.6e-3 | 1.2e-2 | -9.0e-5 | -3.7e-2 | 1.2e-5 | 3.1e-2 | -7.2e-6 | -8.0e-3 | -3.7e-7 | -9.2e-4
2.777 | -6.9e-3 | -2.1e-3 | -2.3e-2 | 1.3e-4 | -2.4e-2 | -8.6e-6 | 3.3e-2 | -3.2e-6 | -8.8e-3 | -1.2e-6 | -9.3e-4
3.010 | -7.6e-3 | 3.4e-3 | 5.4e-3 | -1.4e-6 | -1.7e-2 | -1.2e-5 | 3.5e-2 | 1.2e-6 | -9.5e-3 | -1.9e-6 | -9.3e-4
3.226 | -8.4e-3 | 2.1e-3 | 3.6e-2 | 8.9e-5 | -9.9e-3 | -7.5e-6 | 3.6e-2 | 3.4e-7 | -1.0e-2 | -1.9e-6 | -9.3e-4
3.432 | -9.1e-3 | 3.1e-3 | 4.1e-2 | 2.6e-4 | -3.6e-3 | 1.7e-5 | 3.8e-2 | -3.8e-6 | -1.1e-2 | -1.6e-6 | -9.2e-4
3.533 | -9.5e-3 | -1.7e-3 | 2.6e-2 | 7.3e-5 | -3.6e-4 | -1.6e-5 | 3.8e-2 | -5.5e-7 | -1.1e-2 | -1.8e-6 | -9.0e-4
Errors in multipoles due to cooldown and Lorenz forces:
Max error due to cooldown and Lorenz forces in b2 ~0.1 units

## Slide 14: 3-D FEA to simulate deflections from axial forces on end windings
Presentation this afternoon by James Gerity
The end windings are supported in a nest of G-11 forms, bolted to the
SS bars and beam tube and vacuum-impregnated with filled epoxy.
Only the end region is impregnated.
Deflections due to Lorentz forces on ends are shown. G-11 support matrix is suppressed in this image for clarity.
Maximum displacement ~ 4 µm

## Slide 15
2.5d thermal model of MEIC dipole and cooling scheme: 2d heat transfer in solids +1d in the cooling channels
Assumed heat density, total 0.15 W/m
Isolated Region used in 2-D thermal,
Tij LHe temperatures at far end of the cooling channel
Far side
Near side
Average Heat flux from tube to LHe used in 2-D thermal model, T- tube temperature, Tb, Te – Lhe temperatures at Near and far side of the tube
Cooling channel numbering
Total heat taken by Lhe over half turn
h is enthalpy of LHe

## Slide 16: CIC development for the MEIC dipole
15 NbTi/Cu wires are cabled onto a perforated spring tube.
The cable is inserted in a sheath tube, and the sheath is drawn onto the cable to just compress the wires against the spring tube.

## Slide 17: Superferric Dipoles: How we build them
3. Insert the SS beam tube, seal the ends, and epoxy impregnate the gap between segments and beam tube.
Fabricate inner form segments from 4”-thick G-11 fiber-reinforced epoxy slabs.
Assemble stack of segments for dipole body, using the CIC channels for alignment.
Improvement: Channels for cables are split equally on the facing segments.
Strategy:
All cables are positioned sandwiched between layers of precision-machined structure.
Ends are formed to the side of the dipole, then popped into place in the structure layer.
Overall coil assembly is preloaded within steel flux return, all windings immobilized.

## Slide 18
All ends are formed with 2” radius bends.
1. Bend a U with the correct horizontal spacing.
Bend the U to form a 90° ear, with offset for layer-layer transitions.
‘Odd-man’ turns require forming a ‘dog-bone’ end.
Forming the flared ends requires production tooling
We have validated that bends preserve internal structure, do not damage NbTi wires.

## Slide 19: Impregnated assembly ready for layer 1

## Slide 20: Layer 1 complete

## Slide 21: Caps/forms in place – ready to wind layer 2

## Slide 22: Layer 2 complete

## Slide 23: Caps/forms in place – ready to wind layer 3

## Slide 24: Layer 3 complete

## Slide 25: Final caps in place – preload and QC
Apply flat plates to top/bottom surfaces, clamp sides and top/bottom, dilatometry of x/y cable positions through open slots in G-11 structure.

## Slide 26: Superconducting Wire Spec
Option 1) - Supercon
SC-VSF-SSCI-1.20mm
1.20mm diameter bare
7,240 filaments NbTi @ 9 micron nominal diameter
Cu:SC = 1.5:1
Ic ( 5T, 4.2K): 950 A minimum
Quantity: 4 km
Unit Price: $3,780.00 / km
Option 2) - Supercon
SC-VSF-678-1.20mm
1.20 mm diameter bare
678 filaments NbTi @ 33 micron nominal diameter
Cu:SC = 0.9:1
Ic ( 5T, 4.2K): 1,500 A minimum
Quantity: 4 km
Unit Price: $3,865.00 / km

## Slide 27: Fabrication of G-11 piece-parts
quoted parts | closely related parts |  |  | drawings to Precision | priority for fab | Price |  | 
HEAP-B-55-100-003 |  | 2 | Extension from body - 1 | ✓ | 1 | 255 |  | 510
 | HEAP-B-55-100-032 | 2 | End extension - 2 | ✓ | 1 |  | 255 | 510
HEAP-B-55-100-005 |  | 6 | Middle winding form - short | ✓ | 3 | 92 |  | 552
HEAP-B-55-100-006 |  | 16 | Middle winding form - long | ✓ | 3 | 75 |  | 1200
HEAP-B-55-100-007 |  | 16 | Outer winding form A - long | ✓ | 4 | 65 |  | 1040
 | HEAP-B-55-100-038 | 1 | Outer winding form A - heater cut |  | 4 |  | 65 | 65
HEAP-B-55-100-009 |  | 16 | Cap B - long | ✓ | 5 | 50 |  | 800
 | HEAP-B-55-100-008 | 6 | Cap A |  | 5 |  | 65 | 390
 | HEAP-B-55-100-039 | 1 | Cap - heater cut |  | 5 |  | 65 | 65
HEAP-B-55-100-012 |  | 1 | End form lead 1A | ✓ | 2 | 270 |  | 270
 | HEAP-B-55-100-015 | 1 | End form tail 1A | ✓ | 2 |  | 270 | 270
 | HEAP-B-55-100-024 | 1 | End form tail 2A | ✓ | 2 |  | 270 | 270
 | HEAP-B-55-100-021 | 1 | End form lead 2A | ✓ | 2 |  | 270 | 270
HEAP-B-55-100-013 |  | 1 | End form lead 1B | ✓ | 3 | 250 |  | 250
 | HEAP-B-55-100-016 | 1 | End form tail 1B |  | 3 |  | 250 | 250
 | HEAP-B-55-100-025 | 1 | End form tail 2B |  | 3 |  | 250 | 250
 | HEAP-B-55-100-022 | 1 | End form lead 2B |  | 3 |  | 250 | 250
HEAP-B-55-100-014 |  | 1 | End form lead 1C REV B | ✓ | 4 | 230 |  | 230
 | HEAP-B-55-100-017 | 1 | End form tail 1C REV-B | ✓ | 4 |  | 230 | 230
 | HEAP-B-55-100-027 | 1 | End form tail 2D REV B | ✓ | 4 |  | 230 | 230
 | HEAP-B-55-100-023 | 1 | End form lead 2C |  | 4 |  | 230 | 230
 | HEAP-B-55-100-026 | 1 | End form tail 2C REV B | ✓ | 4 |  | 230 | 230
HEAP-B-55-100-020 |  | 5 | Central winding form | ✓ | 1 | 430 |  | 2150
 | HEAP-B-55-100-019 | 1 | Central winding form - heater cut | ✓ | 1 |  | 430 | 430
 | HEAP-B-55-100-058-REV B | 6 | Central winding form - shoulder cut |  | 1 |  | 430 | 2580
HEAP-B-55-100-030 |  | 1 | Lead end flag 3 left | ✓ | 4 | 120 |  | 120
 | HEAP-B-55-100-033 | 1 | Lead end flag 1 left | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-034 | 1 | Lead end flag 2 left |  | 3 |  | 120 | 120
 | HEAP-B-55-100-035 | 1 | Lead end flag 1 right | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-036 | 1 | Lead end flag 2 right |  | 3 |  | 120 | 120
 | HEAP-B-55-100-037 | 1 | Lead end flag 3 right |  | 4 |  | 120 | 120
 | HEAP-B-55-100-040 | 1 | Lead end flag 4 left | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-041 | 1 | Lead end flag 5 left |  | 3 |  | 120 | 120
 | HEAP-B-55-100-042 | 1 | Lead end flag 6 left |  | 4 |  | 120 | 120
 | HEAP-B-55-100-043 | 1 | Lead end flag 4 right | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-044 | 1 | Lead end flag 5 right |  | 3 |  | 120 | 120
 | HEAP-B-55-100-045 | 1 | Lead end flag 6 right |  | 4 |  | 120 | 120
 | HEAP-B-55-100-046 | 1 | Tail end flag 1 left | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-047 | 1 | Tail end flag 2 left |  | 3 |  | 120 | 120
 | HEAP-B-55-100-048 | 1 | Tail end flag 3 left |  | 4 |  | 120 | 120
 | HEAP-B-55-100-049 | 1 | Tail end flag 1 right | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-050 | 1 | Tail end flag 2 right |  | 3 |  | 120 | 120
 | HEAP-B-55-100-051 | 1 | Tail end flag 3 right |  | 4 |  | 120 | 120
 | HEAP-B-55-100-052 | 1 | Tail end flag 4 right | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-053 | 1 | Tail end flag 5 right |  | 3 |  | 120 | 120
 | HEAP-B-55-100-054 | 1 | Tail end flag 6 right |  | 4 |  | 120 | 120
 | HEAP-B-55-100-055 | 1 | Tail end flag 4 left | ✓ | 2 |  | 120 | 120
 | HEAP-B-55-100-056 | 1 | Tail end flag 5 left |  | 3 |  | 120 | 120
 | HEAP-B-55-100-057 | 1 | Tail end flag 6 left |  | 4 |  | 120 | 120
HEAP-B-55-100-031 |  | 1 | Middle wind form A heater cut |  | 3 | 145 |  | 145
 | HEAP-B-55-100-059 |  | Tail end flag 7 left |  |  |  |  | 
 | HEAP-B-55-100-060 |  | Mockup winding assembly | ✓ |  |  |  | 16547

## Slide 28: QC of G-11 window-frame assembly

## Slide 29: Central winding form – no QC channels

## Slide 31
Central winding form – with QC channels

## Slide 32: Central winding form – heater channels

## Slide 33: Quench Protection
Quench heater foils are bonded in a 10 cm end segment of the G-11 structure on both ends of the dipole.
Every cable turn is driven normal in ~10 ms by a current pulse to the heater foils.
Chart: Peak Temperature
Chart: MIITs
Talk this afternoon by Daniel Chavez

## Slide 34: Provision for differential contraction, preload against Lorentz forces in body
Horizontal contraction
Chart: Central Multipoles Cold+Forces @2cm
| 0.18723999999999999 | 0.37462000000000001 | 0.74938000000000005 | 1.1240699999999999 | 1.4982899999999999 | 1.86812 | 2.2139000000000002 | 2.51946 | 2.7833600000000001 | 3.0171700000000001 | 3.2340200000000001 | 3.44123 | 3.54284
b2 | 0.23362 | 0.2032 | 0.15959 | 0.12656 | 0.16161 | 0.6489 | 0.71925 | 0.12544 | -0.71964 | -0.42286 | 0.8218 | 2.5409 | 3.5519
b4 | -1.0319 | -1.0328 | -1.0316 | -1.0301 | -1.0276 | -1.0507 | -1.0782 | -1.0287 | -0.83787 | -0.66137 | -0.50464 | -0.35998 | -0.29151
b6 | 1.0677 | 1.067 | 1.0666 | 1.0664 | 1.0653 | 1.068 | 1.0971 | 1.1826 | 1.2908 | 1.3972 | 1.4938 | 1.5805 | 1.6206
b8 | -0.33758 | -0.33744 | -0.33741 | -0.33747 | -0.33733 | -0.33692 | -0.33898 | -0.35037 | -0.36819 | -0.38702 | -0.40512 | -0.4221 | -0.43011
Orient G-11 with fabric perpendicular to beam tube axis – small contraction.
Locate Ti U-channels to compensate differential contraction – warm-cold ~+.002”
Locate SS/mica paper slip plane between G-11 and steel flux return.
Ti
G-11
316 SS
Steel

## Slide 35: CIC Winding limits temperature rise in event of heat from beam losses
Simulated temperature distribution in the presence of 0.5 W heat deposition in a 4 m MEIC dipole winding.
4.5 K
4.4
4.3
4.2
CIC Structure controls Lorentz stress to prevent coil motion, training, error fields
Y displacement (RT – 3 T) .001”
X displacement (RT – 3 T) .001”
Multipole effects <0.2 units

## Slide 36: Present status
We have improved the magnetic design so that all multipoles are <1 unit over operating range.
We have incorporated preload and differential contraction compensation so that preload is preserved over cool-down.
We have completed and impregnated the structural beam, ready to wind layer 1.
We have fabricated and assembled the two main motorized benders, and are programming their operations.
We have prepared the winding supports for cable, tensioner, and winding assembly.
We have formed sample cables with the several candidates for central core tube, tested Ic on extracted strands, validated that there is no strain degradation.